## Test
ID	Event	Content option	Status 2011/07/12	Status 2012/01/12	Comments
1	ADDLOCATION	a simple folder	KO	gg: partially fixed in commit cbeaad0e1e, final fixes in bce8a50c4	Fatal error: Call to protected method contentStagingBase::encodeSortField() from context 'eZRestApiGGWSClientStagingTransport' in D:\wamp\www\ez1\extension\ezcontentstaging\classes\ezrestapiggwsclientstagingtransport.php on line 214 / Sync status : sync ongoing ... => ???
2	DELETE	a simple folder	KO	gg: fixed in commit f3d0dbde	pas de message d'erreur mais le folder n'a pas été supprimé sur la destination
3	HIDEUNHIDE	a simple folder	KO	gg: fixed in commit 697f268	Object 183 to be synchronised to feed pippo: failure (HTTP error (HTTP/1.1 400 Bad Request)) [Event 38]
4	MOVE	a simple folder	KO	gg: fixed in commit 29cb1e5	But the content has not moved on the destination
5	PUBLISH	a simple folder	OK
6	REMOVELOCATION
7	REMOVETRANSLATION			to finish...
8	SORT	Sort a simple folder by published date ASC	KO	gg: possibily fixed in commit cbeaad0e1e, final fixes in 993acba	Fatal error: Call to protected method contentStagingBase::encodeSortField() from context 'eZRestApiGGWSClientStagingTransport' in D:\wamp\www\ez1\extension\ezcontentstaging\classes\ezrestapiggwsclientstagingtransport.php on line 214 / Sync status : sync ongoing ... => ???
9	SWAP
10	UPDATEALWAYSAVAILABLE
11	UPDATEINITIALLANGUAGE	main language updated on a simple forder between french to english		gg: fixed in commit e9cb441	Object 181 to be synchronised to feed pippo: failure (Response received from server is not valid (unsupported format text/html)) [Event 42]
12	UPDATEMAINASSIGNMENT
13	UPDATEOBJECSTATE
14	UPDATEPRIORITY
15	UPDATESECTION
16	INITIALIZEFEED	OK
17	Add translation	a simple folder	OK		NB: if added language does not exist on target server, no error is reported. Is this ok ?
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99

## bugs
ID	Summary	Description	Reporter	Environnement	Comments	Created	Resolved	Status
1	Delete a content associated with stage delete event	Fatal error: Call to a member function attribute() on a non-object in D:\wamp\www\ez1\extension\ezcontentstaging\eventtypes\event\ezstagedelete\ezstagedeletetype.php on line 58 / Fatal error: eZ Publish did not finish its request	jlemaitre	Windows XP, PHP 5.3.5, eZPublish4.5	I have replaced the ligne 57 / $object = $node->attribute( 'contentobject' ); / By / $object = $node->ContentObject;	25/11/11	Fixed 28/11/2011 in commit b119971f3,	resolved
2	Delete a content associated with stage delete event	$trash = $parameres['move_to_trash']; on line 31 is null. The trash value in the ezcontentstaging_event.data_text colum is also always null.	jlemaitre	Windows XP, PHP 5.3.5, eZPublish4.5		30/11/11		resolved
3	Synchronization of a embedded content – Permission error	On my source, I have created 2 objects under the root node. The first one is a folder that includes article as a embedded object in the description attribute. / After synchronisation. I do not view the embedded article in the description of the folder due to the next error "You do not have permission to view this object". / You get this error detail when you edit the new folder on the target server. / I have connected as admin.	jlemaitre	Windows XP, PHP 5.3.5, eZPublish4.5		01/12/11		new
4	Move an article	I move the article on the root node to sub folder. I have the following error : Fatal error: Function name must be a string in D:\wamp\www\ez1\extension\ezcontentstaging\eventtypes\event\ezstagemove\ezstagemovetype.php on line 46 / Fatal error: eZ Publish did not finish its request	jlemaitre	Windows XP, PHP 5.3.5, eZPublish4.5		01/12/11	Fixed 28/11/2011 in commit b119971f3,	resolved
5	Delete an object, when there is already a sync event for it	In the dashboard, object name and other data are not displayed	gg	Windows 7, PHP 5.3.8, eZP 4.5	This happens because we store obj name only in delete event, and currently the dashboard block template takes the first event for that node to show things. Could be fixed if we delete all pending events for the node (or we forbid deletion)	02/12/11		open
6	Add a location for an object, when there are already one or more sync events for it	The new locations will not show the existing events, even for those types of events which apply to all nodes of an event	gg	Windows 7, PHP 5.3.8, eZP 4.5	This happens because we store the list of affacted nodes in the db tables relating to events. / Proposed fix: on the add locations / delete locations triggers also update those tables	05/12/11		open
7	Simple article publication	I have just fill the name, summary and description with raw data. / Error sync message : Object 172 to be synchronised to feed pippo: failure (Response received from server is not valid (unsupported format text/html)) [Event 16]	jlemaitre	Windows XP, PHP 5.3.5, eZPublish4.5	The content been correctly published to the destination
8	Simple folder publication	I have just fill the name, shortname, summary, description with simple formed text and tags. / Object 173 to be synchronised to feed pippo: failure (Response received from server is not valid (unsupported format text/html)) [Event 17]	jlemaitre	Windows XP, PHP 5.3.5, eZPublish4.5	The folder has not been published to the destination
9	Move a folder in another one	I have move a folder into another one. I have no error but the folder has not moved on the destination. / Sync lsg : Object 176 succesfully synchronised to feed pippo [Event 24]	jlemaitre	Windows XP, PHP 5.3.5, eZPublish4.5
10	Sort a folder by publish date	Fatal error: Call to protected method contentStagingBase::encodeSortField() from context 'eZRestApiGGWSClientStagingTransport' in D:\wamp\www\ez1\extension\ezcontentstaging\classes\ezrestapiggwsclientstagingtransport.php on line 214 / After refreshing the page, I have the following error / Error : content synchronisation action results : / Object 171 to be synchronised to feed pippo: failure (Can not sync event: not in pending status. Status: 1) [Event 27]	jlemaitre	Windows XP, PHP 5.3.5, eZPublish4.5
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99